## Wait Times
Team | Data Product ID | Data Product Name | Table | Location | Fulcrum load delay | Transition wait time | Latency category | Legacy ingest status (%) | Legacy delay driver | Expected Legacy Ingest Completion | Legacy Data notes
TOS | NEON.DOM.SITE.DP1.10003.001 | Breeding landbird point counts | brd_countdata_pub | External | NA | 45 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10003.001 | Breeding landbird point counts | brd_perpoint_pub | External | NA | 45 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10003.001 | Breeding landbird point counts | brd_personnel_pub | External | NA | 45 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10003.001 | Breeding landbird point counts | brd_references_pub | External | NA | 45 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10035.001 | Bryophyte clip harvest | bry_productivity_pub | Field | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10014.001 | Coarse downed wood bulk density sampling | cdw_densitydisk_pub | Field | 90 | 105 | DD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to ingest final error corrected records
TOS | NEON.DOM.SITE.DP1.10014.001 | Coarse downed wood bulk density sampling | cdw_densitylog_pub | Field | 90 | 105 | DD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to ingest final error corrected records
TOS | NEON.DOM.SITE.DP1.10010.001 | Coarse downed wood log survey | cdw_fieldtally_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to ingest final error corrected records
TOS | NEON.DOM.SITE.DP1.10017.001 | Digital hemispheric photos of plot vegetation | dhp_perimagefile_pub | Field | NA | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10017.001 | Digital hemispheric photos of plot vegetation | dhp_perplot_pub | Field | NA | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10020.001 | Ground beetle sequences DNA barcode | bet_BOLDcollectionData_pub | External | NA | 614 | ELS | 56 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10020.001 | Ground beetle sequences DNA barcode | bet_BOLDspecimenDetails_pub | External | NA | 614 | ELS | 56 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10020.001 | Ground beetle sequences DNA barcode | bet_BOLDtaxonomy_pub | External | NA | 614 | ELS | 56 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10020.001 | Ground beetle sequences DNA barcode | bet_BOLDvoucherInfo_pub | External | NA | 614 | ELS | 56 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_archivepooling_pub | Domain | 300 | 330 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_expertTaxonomistIDProcessed_pub | External | NA | 600 | ELS | 100 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_expertTaxonomistIDRaw_pub | External | NA | 600 | ELS | 100 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_fielddata_pub | Field | 60 | 75 | FD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_parataxonomistID_pub | Domain | 300 | 330 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10022.001 | Ground beetles sampled from pitfall traps | bet_sorting_pub | Domain | 300 | 330 | ELS | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10023.001 | Herbaceous clip harvest | hbp_massdata_pub | Domain | 45 | 60 | DD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to ingest final error corrected records
TOS | NEON.DOM.SITE.DP1.10023.001 | Herbaceous clip harvest | hbp_perbout_pub | Field | 45 | 60 | DD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to ingest final error corrected records
TOS | NEON.DOM.SITE.DP1.10031.001 | Litter chemical properties | ltr_litterCarbonNitrogen_pub | External | NA | 270 | ELF | 60 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10031.001 | Litter chemical properties | ltr_litterLignin_pub | External | NA | 120 | ELF | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10101.001 | Litter stable isotopes | ltr_litterStableIsotopes_pub | External | NA | 270 | ELF | 30 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10033.001 | Litterfall and fine woody debris sampling | ltr_chemistrySubsampling_pub | Domain | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10033.001 | Litterfall and fine woody debris sampling | ltr_fielddata_pub | Field | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10033.001 | Litterfall and fine woody debris sampling | ltr_massdata_pub | Domain | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10033.001 | Litterfall and fine woody debris sampling | ltr_pertrap_pub | Field | 14 | 30 | FD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10038.001 | Mosquito sequences DNA barcode | mos_BOLDcollectionData_pub | External | NA | 255 | ELS | 7 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10038.001 | Mosquito sequences DNA barcode | mos_BOLDspecimenDetails_pub | External | NA | 255 | ELS | 7 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10038.001 | Mosquito sequences DNA barcode | mos_BOLDtaxonomy_pub | External | NA | 255 | ELS | 7 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10038.001 | Mosquito sequences DNA barcode | mos_BOLDvoucherInfo_pub | External | NA | 255 | ELS | 7 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10041.001 | Mosquito-borne pathogen status | mos_pathogenpooling_pub | External | NA | 360 | ELS | 6 | contracting | 2018-12-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10041.001 | Mosquito-borne pathogen status | mos_pathogenresults_pub | External | NA | 360 | ELS | 6 | contracting | 2018-12-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_archivepooling_pub | External | NA | 240 | ELS | 70 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to correct sampleID errors that allow for data ingest
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_barcoding_pub | External | NA | 420 | ELS | 7 | contracting | 2018-12-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_expertTaxonomistIDProcessed_pub | External | NA | 240 | ELS | 70 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to correct sampleID errors that allow for data ingest
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_expertTaxonomistIDRaw_pub | External | NA | 240 | ELS | 70 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to correct sampleID errors that allow for data ingest
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_sorting_pub | External | NA | 240 | ELS | 100 | NA
TOS | NEON.DOM.SITE.DP1.10043.001 | Mosquitoes sampled from CO2 traps | mos_trapping_pub | Field | 14 | 30 | ELF | 100 | NA
TOS | NEON.DOM.SITE.DP1.10045.001 | Non-herbaceous perennial vegetation structure | nst_perindividual_pub | Field | 75 | 90 | FD | 90 | field science resources | 2018-12-31 | Waiting for field staff to conduct protocol again to efficiently resolve errors
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_carbonNitrogen_pub | External | NA | 270 | ELF | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_chemistrySubsampling_pub | Domain | 45 | 60 | DD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_chlorophyll_pub | External | NA | 120 | ELF | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_elements_pub | External | NA | 270 | ELF | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_fieldData_pub | Field | 30 | 45 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_lignin_pub | External | NA | 120 | ELF | 100 | NA
TOS | NEON.DOM.SITE.DP1.10026.001 | Plant foliar physical and chemical properties | cfc_LMA_pub | Domain | 45 | 60 | DD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10053.001 | Plant foliar stable isotopes | cfc_foliarStableIsotopes_pub | External | NA | 270 | ELF | 75 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10055.001 | Plant phenology observations | phe_perindividual_pub | Field | 14 | 30 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10055.001 | Plant phenology observations | phe_perindividualperyear_pub | Field | 14 | 30 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10055.001 | Plant phenology observations | phe_statusintensity_pub | Field | 14 | 30 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10058.001 | Plant presence and percent cover | div_10m2Data100m2Data_pub | Field | 120 | 135 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10058.001 | Plant presence and percent cover | div_1m2Data_pub | Field | 120 | 135 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10058.001 | Plant presence and percent cover | div_geneticarchive_pub | Field | 14 | 30 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10058.001 | Plant presence and percent cover | div_voucher_pub | Field | 14 | 30 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10064.001 | Rodent-borne pathogen status | rpt_bloodtesting_pub | External | NA | 270 | ELF | 60 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to conduct QA and upload 2017 data
TOS | NEON.DOM.SITE.DP1.10102.001 | Root chemical properties | bbc_rootChemistry_pub | External | NA | 270 | ELF | 50 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10066.001 | Root sampling (Megapit) | mpr_perdepthincrement_pub | External | NA | NA | OT | 80 | external lab processing | 2018-09-30 | MBL lab not returning soil data on time; samples backlogged; dependency
TOS | NEON.DOM.SITE.DP1.10066.001 | Root sampling (Megapit) | mpr_perpitprofile_pub | External | NA | NA | OT | 80 | external lab processing | 2018-09-30 | MBL lab not returning soil data on time; samples backlogged; dependency
TOS | NEON.DOM.SITE.DP1.10066.001 | Root sampling (Megapit) | mpr_perrootsample_pub | External | NA | NA | OT | 80 | external lab processing | 2018-09-30 | MBL lab not returning soil data on time; samples backlogged; dependency
TOS | NEON.DOM.SITE.DP1.10067.001 | Root sampling tower plots | bbc_chemistryPooling_pub | Domain | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10067.001 | Root sampling tower plots | bbc_dilution_pub | Domain | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10067.001 | Root sampling tower plots | bbc_percore_pub | Field | 45 | 60 | FD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10067.001 | Root sampling tower plots | bbc_rootmass_pub | Domain | 45 | 60 | DD | 100 | NA | NA
TOS | NEON.DOM.SITE.DP1.10099.001 | Root stable isotopes | bbc_rootStableIsotopes_pub | External | NA | 270 | ELF | 50 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10072.001 | Small mammal box trapping | mam_perplotnight_pub | Field | 30 | 45 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10072.001 | Small mammal box trapping | mam_pertrapnight_pub | Field | 30 | 45 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10072.001 | Small mammal box trapping | mam_voucher_pub | Field | 30 | 45 | FD | 100 | NA
TOS | NEON.DOM.SITE.DP1.10076.001 | Small mammal sequences DNA barcode | mam_BOLDcollectionData_pub | External | NA | 375 | ELS | 6 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10076.001 | Small mammal sequences DNA barcode | mam_BOLDspecimenDetails_pub | External | NA | 375 | ELS | 6 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10076.001 | Small mammal sequences DNA barcode | mam_BOLDtaxonomy_pub | External | NA | 375 | ELS | 6 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10076.001 | Small mammal sequences DNA barcode | mam_BOLDvoucherInfo_pub | External | NA | 375 | ELS | 6 | contracting | 2018-10-31 | Vendor identified; contracting process prolonged
TOS | NEON.DOM.SITE.DP1.10008.001 | Soil chemical properties (Distributed initial characterization) | spc_biogeochem_pub | External | NA | NA | OT | 15 | external lab processing | 2018-12-31 | NRCS not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10078.001 | Soil chemical properties (Distributed periodic) | sls_soilChemistry_pub | External | NA | 270 | ELF | 95 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00097.001 | Soil chemical properties (Megapit) | mgc_perarchivesample_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00097.001 | Soil chemical properties (Megapit) | mgc_perbiogeosample_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00097.001 | Soil chemical properties (Megapit) | mgc_perhorizon_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00097.001 | Soil chemical properties (Megapit) | mgc_permegapit_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10080.001 | Soil inorganic nitrogen pools and transformations | ntr_externalLab_pub | External | NA | 270 | ELF | 70 | external lab processing | 2018-09-30 | EcoCore not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10080.001 | Soil inorganic nitrogen pools and transformations | ntr_internalLab_pub | Domain | 45 | 60 | DD | 70 | external lab processing | 2018-09-30 | EcoCore not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10080.001 | Soil inorganic nitrogen pools and transformations | ntr_internalLabBlanks_pub | Domain | 45 | 60 | DD | 70 | external lab processing | 2018-09-30 | EcoCore not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10104.001 | Soil microbe biomass | sme_batchResults_pub | External | NA | 14 | ELF | 1 | external lab processing | 2018-08-31 | EcoCore not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10104.001 | Soil microbe biomass | sme_microbialBiomass_pub | External | NA | 240 | ELF | 1 | external lab processing | 2018-08-31 | EcoCore not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10081.001 | Soil microbe community composition | mcc_soilTaxonTable_pub | External | NA | 240 | ELF | 2 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10109.001 | Soil microbe group abundances | mga_batchResults_pub | External | NA | 14 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10109.001 | Soil microbe group abundances | mga_soilGroupAbundances_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10108.001 | Soil microbe marker gene sequences | mmg_soilDnaExtraction_pub | External | NA | 240 | ELF | 6 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10108.001 | Soil microbe marker gene sequences | mmg_soilMarkerGeneSequencing_16S_pub | External | NA | 240 | ELF | 6 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10108.001 | Soil microbe marker gene sequences | mmg_soilMarkerGeneSequencing_ITS_pub | External | NA | 240 | ELF | 6 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10108.001 | Soil microbe marker gene sequences | mmg_soilPcrAmplification_16S_pub | External | NA | 240 | ELF | 6 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10108.001 | Soil microbe marker gene sequences | mmg_soilPcrAmplification_ITS_pub | External | NA | 240 | ELF | 6 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10107.001 | Soil microbe metagenome sequences | mms_metagenomeDnaExtraction_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10107.001 | Soil microbe metagenome sequences | mms_metagenomeSequencing_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
TOS | NEON.DOM.SITE.DP1.10047.001 | Soil physical properties (Distributed initial characterization) | spc_bulkdensity_pub | External | NA | NA | OT | 15 | external lab processing | 2018-12-31 | NRCS not returning data on time
TOS | NEON.DOM.SITE.DP1.10047.001 | Soil physical properties (Distributed initial characterization) | spc_particlesize_pub | External | NA | NA | OT | 15 | external lab processing | 2018-12-31 | NRCS not returning data on time
TOS | NEON.DOM.SITE.DP1.10047.001 | Soil physical properties (Distributed initial characterization) | spc_perhorizon_pub | External | NA | NA | OT | 15 | external lab processing | 2018-12-31 | NRCS not returning data on time
TOS | NEON.DOM.SITE.DP1.10047.001 | Soil physical properties (Distributed initial characterization) | spc_perplot_pub | External | NA | NA | OT | 15 | external lab processing | 2018-12-31 | NRCS not returning data on time
TOS | NEON.DOM.SITE.DP1.10086.001 | Soil physical properties (Distributed periodic) | sls_bgcSubsampling_pub | Domain | 45 | 60 | DD | 95 | science resources | 2018-05-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
TOS | NEON.DOM.SITE.DP1.10086.001 | Soil physical properties (Distributed periodic) | sls_metagenomicsPooling_pub | Domain | 30 | 45 | DD | 95 | science resources | 2018-05-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
TOS | NEON.DOM.SITE.DP1.10086.001 | Soil physical properties (Distributed periodic) | sls_soilCoreCollection_pub | Field | 30 | 45 | FD | 95 | science resources | 2018-05-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
TOS | NEON.DOM.SITE.DP1.10086.001 | Soil physical properties (Distributed periodic) | sls_soilMoisture_pub | Domain | 45 | 60 | DD | 95 | science resources | 2018-05-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
TOS | NEON.DOM.SITE.DP1.10086.001 | Soil physical properties (Distributed periodic) | sls_soilpH_pub | Domain | 45 | 60 | DD | 95 | science resources | 2018-05-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
TOS | NEON.DOM.SITE.DP1.00096.001 | Soil physical properties (Megapit) | mgp_perarchivesample_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00096.001 | Soil physical properties (Megapit) | mgp_perbiogeosample_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00096.001 | Soil physical properties (Megapit) | mgp_perbulksample_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00096.001 | Soil physical properties (Megapit) | mgp_perhorizon_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.00096.001 | Soil physical properties (Megapit) | mgp_permegapit_pub | External | NA | NA | OT | 75 | external lab processing | 2018-09-30 | MBL lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10100.001 | Soil stable isotopes (Distributed periodic) | sls_soilStableIsotopes_pub | External | NA | 270 | ELF | 95 | external lab processing | 2018-09-30 | U WY lab not returning data on time; samples backlogged
TOS | NEON.DOM.SITE.DP1.10092.001 | Tick-borne pathogen status | tck_pathogen_pub | External | NA | 390 | ELS | 100 | NA | NA | NA
TOS | NEON.DOM.SITE.DP1.10092.001 | Tick-borne pathogen status | tck_pathogenqa_pub | External | NA | 390 | ELS | 100 | NA | NA | NA
TOS | NEON.DOM.SITE.DP1.10093.001 | Ticks sampled using drag cloths | tck_fielddata_pub | Field | 14 | 30 | FD | 75 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to conduct QA and upload 2017 data
TOS | NEON.DOM.SITE.DP1.10093.001 | Ticks sampled using drag cloths | tck_taxonomyProcessed_pub | External | NA | 300 | ELS | 75 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to conduct QA and upload 2017 data
TOS | NEON.DOM.SITE.DP1.10093.001 | Ticks sampled using drag cloths | tck_taxonomyRaw_pub | External | NA | 300 | ELS | 75 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to conduct QA and upload 2017 data
TOS | NEON.DOM.SITE.DP1.10098.001 | Woody plant vegetation structure | vst_apparentindividual_pub | Field | 75 | 90 | FD | 90 | field science resources | 2018-12-31 | Waiting for field staff to conduct protocol again to resolve errors
TOS | NEON.DOM.SITE.DP1.10098.001 | Woody plant vegetation structure | vst_mappingandtagging_pub | Field | 75 | 90 | FD | 90 | field science resources | 2018-12-31 | Waiting for field staff to conduct protocol again to resolve errors
TOS | NEON.DOM.SITE.DP1.10098.001 | Woody plant vegetation structure | vst_perplotperyear_pub | Field | 270 | 300 | FD | 90 | field science resources | 2018-12-31 | Waiting for field staff to conduct protocol again to resolve errors
TOS | NEON.DOM.SITE.DP1.10098.001 | Woody plant vegetation structure | vst_shrubgroup_pub | Field | 75 | 90 | FD | 90 | field science resources | 2018-12-31 | Waiting for field staff to conduct protocol again to resolve errors
AOS | NEON.DOM.SITE.DP1.20063.001 | Aquatic plant bryophyte chemical properties | apl_plantExternalLabDataPerSample_pub | External | NA | 180 | ELF | 100 | NA | NA | NA
AOS | NEON.DOM.SITE.DP1.20066.001 | Aquatic plant bryophyte macroalgae clip harvest | apl_biomass_pub | Domain | 45 | 60 | DD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
AOS | NEON.DOM.SITE.DP1.20066.001 | Aquatic plant bryophyte macroalgae clip harvest | apl_clipHarvest_pub | Field | 45 | 60 | FD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction of 2013 data
AOS | NEON.DOM.SITE.DP1.20066.001 | Aquatic plant bryophyte macroalgae clip harvest | apl_taxonomyProcessed_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20066.001 | Aquatic plant bryophyte macroalgae clip harvest | apl_taxonomyRaw_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_morphospecies_pub | Domain | 360 | 390 | DD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_perTaxon_pub | Field | 45 | 60 | FD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_pointTransect_pub | Field | 45 | 60 | FD | 90 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_taxonomyProcessed_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_taxonomyRaw_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_voucher_pub | Domain | 14 | 30 | DD | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_voucherTaxonomyProcessed_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20072.001 | Aquatic plant, bryophyte, lichen, and macroalgae point counts in wadeable streams | apc_voucherTaxonomyRaw_pub | External | NA | 240 | ELF | 25 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP4.00132.001 | Bathymetric and morphological maps | bat_fieldData_pub | Field | 42 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00132.001 | Bathymetric and morphological maps | bat_pointcollection_pub | Field | 42 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00132.001 | Bathymetric and morphological maps | bat_sonarRecord_pub | Field | 42 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00132.001 | Bathymetric and morphological maps | bat_resultsFile_pub | HQ | NA | 180 | DD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP1.20086.001 | Benthic microbe community composition | mcc_benthicTaxonTable_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20277.001 | Benthic microbe group abundances | mga_benthicGroupAbundances_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | amb_fieldParent_pub | Field | 45 | 60 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | mmg_benthicDnaExtraction_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | mmg_benthicMarkerGeneSequencing_16S_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | mmg_benthicMarkerGeneSequencing_ITS_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | mmg_benthicPcrAmplification_16S_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20280.001 | Benthic microbe marker gene sequences | mmg_benthicPcrAmplification_ITS_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20279.001 | Benthic microbe metagenome sequences | amb_fieldParent_pub | Field | 45 | 60 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20279.001 | Benthic microbe metagenome sequences | mms_benthicMetagenomeDnaExtraction_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20279.001 | Benthic microbe metagenome sequences | mms_benthicMetagenomeSequencing_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20092.001 | Chemical properties of groundwater | gwc_domainLabData_pub | Domain | 28 | 60 | DD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20092.001 | Chemical properties of groundwater | gwc_externalLabData_pub | External | NA | 150 | ELF | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20092.001 | Chemical properties of groundwater | gwc_fieldData_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20092.001 | Chemical properties of groundwater | gwc_fieldSuperParent_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20093.001 | Chemical properties of surface water | swc_domainLabData_pub | Domain | 28 | 60 | DD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20093.001 | Chemical properties of surface water | swc_externalLabData_pub | External | NA | 150 | ELF | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20093.001 | Chemical properties of surface water | swc_fieldData_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20093.001 | Chemical properties of surface water | swc_fieldSuperParent_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20254.001 | Depth profile at specific depths | dep_profileData_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20254.001 | Depth profile at specific depths | dep_profileHeader_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20097.001 | Dissolved gases in surface water | sdg_externalLabData_pub | External | NA | 120 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20097.001 | Dissolved gases in surface water | sdg_fieldData_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20097.001 | Dissolved gases in surface water | sdg_fieldDataAir_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20097.001 | Dissolved gases in surface water | sdg_fieldDataProc_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20097.001 | Dissolved gases in surface water | sdg_fieldSuperParent_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20107.001 | Fish electrofishing, gill netting, and fyke netting counts | fsh_bulkCount_pub | Field | 30 | 45 | FD | 10 | science resources | 2018-08-31 | Waiting on field scientist to complete data entry into Fulcrum and HQ scientist to complete QA
AOS | NEON.DOM.SITE.DP1.20107.001 | Fish electrofishing, gill netting, and fyke netting counts | fsh_fieldData_pub | Field | 30 | 45 | FD | 10 | science resources | 2018-08-31 | Waiting on field scientist to complete data entry into Fulcrum and HQ scientist to complete QA
AOS | NEON.DOM.SITE.DP1.20107.001 | Fish electrofishing, gill netting, and fyke netting counts | fsh_morphospecies_pub | Field | 360 | 390 | FD | 10 | science resources | 2018-08-31 | Waiting on field scientist to complete data entry into Fulcrum and HQ scientist to complete QA
AOS | NEON.DOM.SITE.DP1.20107.001 | Fish electrofishing, gill netting, and fyke netting counts | fsh_perFish_pub | Field | 30 | 45 | FD | 10 | science resources | 2018-08-31 | Waiting on field scientist to complete data entry into Fulcrum and HQ scientist to complete QA
AOS | NEON.DOM.SITE.DP1.20107.001 | Fish electrofishing, gill netting, and fyke netting counts | fsh_perPass_pub | Field | 30 | 45 | FD | 10 | science resources | 2018-08-31 | Waiting on field scientist to complete data entry into Fulcrum and HQ scientist to complete QA
AOS | NEON.DOM.SITE.DP1.20105.001 | Fish sequences DNA barcode | fsh_BOLDcollectionData_pub | External | NA | 390 | ELS | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20105.001 | Fish sequences DNA barcode | fsh_BOLDspecimenDetails_pub | External | NA | 390 | ELS | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20105.001 | Fish sequences DNA barcode | fsh_BOLDtaxonomy_pub | External | NA | 390 | ELS | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20105.001 | Fish sequences DNA barcode | fsh_BOLDvoucherInfo_pub | External | NA | 390 | ELS | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20267.001 | Gauge height | gag_fieldData_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20120.001 | Macroinvertebrate collection | inv_fieldData_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20120.001 | Macroinvertebrate collection | inv_persample_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20120.001 | Macroinvertebrate collection | inv_pervial_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20120.001 | Macroinvertebrate collection | inv_taxonomyProcessed_pub | External | NA | 240 | ELF | 90 | external lab processing | 2018-07-31 | Waiting for final 2017 data from lab
AOS | NEON.DOM.SITE.DP1.20120.001 | Macroinvertebrate collection | inv_taxonomyRaw_pub | External | NA | 240 | ELF | 90 | external lab processing | 2018-07-31 | Waiting for final 2017 data from lab
AOS | NEON.DOM.SITE.DP1.20126.001 | Macroinvertebrate DNA barcode | inv_dnaExtraction_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20126.001 | Macroinvertebrate DNA barcode | inv_markerGeneSequencing_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20126.001 | Macroinvertebrate DNA barcode | inv_pcrAmplification_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20163.001 | Periphyton, seston, and phytoplankton chemical properties | alg_algaeExternalLabDataPerSample_pub | External | NA | 180 | ELF | 100 | NA | NA | SIRFIR lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20163.001 | Periphyton, seston, and phytoplankton chemical properties | alg_domainLabChemistry_pub | Domain | 45 | 60 | DD | 100 | NA | NA | SIRFIR lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20166.001 | Periphyton, seston, and phytoplankton collection | alg_biomass_pub | Domain | 45 | 60 | DD | 65 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20166.001 | Periphyton, seston, and phytoplankton collection | alg_fieldData_pub | Field | 45 | 60 | FD | 65 | science resources | 2018-07-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20166.001 | Periphyton, seston, and phytoplankton collection | alg_taxonomyProcessed_pub | External | NA | 240 | ELF | 20 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20166.001 | Periphyton, seston, and phytoplankton collection | alg_taxonomyRaw_pub | External | NA | 240 | ELF | 20 | external lab processing | 2018-08-31 | Drexel lab working through sample backlog since Sept 2016 - contractually have until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_backgroundFieldCondData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_backgroundFieldSaltData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_conductivityFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_externalLabDataGas_pub | External | NA | 120 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_externalLabDataSalt_pub | External | NA | 120 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_fieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_plateauMeasurementFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_plateauSampleFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20190.001 | Reaeration field and lab collection | rea_widthFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20275.001 | Riparian composition and structure | rip_assessment_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20191.001 | Riparian vegetation % cover | rip_percentComposition_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_backgroundFieldCondData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_backgroundFieldSaltData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_conductivityFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_externalLabDataSalt_pub | External | NA | 120 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_fieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_plateauMeasurementFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20193.001 | Salt-based stream discharge | sbd_plateauSampleFieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20252.001 | Secchi depth | dep_secchi_pub | Field | 14 | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20194.001 | Sediment chemical properties | asc_externalLabData_pub | External | NA | 90 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20194.001 | Sediment chemical properties | asc_fieldDataPoint_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20194.001 | Sediment chemical properties | asc_fieldDataStation_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20194.001 | Sediment chemical properties | asc_fieldDataZone_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20197.001 | Sediment physical properties | asp_externalLabData_pub | External | NA | 90 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20276.001 | Stable isotope concentrations in groundwater | gsi_externalLabH2OIsotopes_pub | External | NA | 120 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20276.001 | Stable isotope concentrations in groundwater | gsi_fieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20276.001 | Stable isotope concentrations in groundwater | gsi_fieldSuperParent_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20206.001 | Stable isotope concentrations in surface waters | asi_externalLabH2OIsotopes_pub | External | NA | 120 | ELF | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20206.001 | Stable isotope concentrations in surface waters | asi_fieldData_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20206.001 | Stable isotope concentrations in surface waters | asi_fieldSuperParent_pub | Field | 14 | 30 | FD | 90 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20206.001 | Stable isotope concentrations in surface waters | asi_POMExternalLabDataPerSample_pub | External | NA | 180 | ELF | 100 | NA | NA | SIRFIR lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20048.001 | Stream discharge field collection | dsc_fieldData_pub | Field | NA | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20048.001 | Stream discharge field collection | dsc_individualFieldData_pub | Field | NA | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20048.001 | Stream discharge field collection | dsc_individualFieldDataADCP_pub | Field | NA | 30 | FD | 100 | NA | NA
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_mappedPointErrors_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_pebbleCount_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_featureInfo_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_totalStation_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_missingLine_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_surveyFieldData_pub | Field | 45 | 60 | FD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_resultsFile_pub | HQ | NA | 120 | DD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_controlInfo_pub | HQ | NA | 120 | DD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_priorParameters_pub | HQ | NA | 120 | DD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP4.00131.001 | Stream morphology map | geo_controlType_pub | HQ | NA | 120 | DD | 10 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to process data to generate maps
AOS | NEON.DOM.SITE.DP1.20138.001 | Surface water microbe cell count | amc_cellCounts_pub | External | NA | 150 | ELF | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20138.001 | Surface water microbe cell count | amc_fieldCellCounts_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20138.001 | Surface water microbe cell count | amc_fieldSuperParent_pub | Field | 14 | 30 | FD | 95 | science resources | 2018-08-31 | Waiting on HQ Scientist availability to complete error correction
AOS | NEON.DOM.SITE.DP1.20141.001 | Surface water microbe community composition | mcc_swTaxonTable_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20278.001 | Surface water microbe group abundances | mga_swGroupAbundances_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | amc_fieldGenetic_pub | Field | 14 | 30 | FD | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | mmg_swDnaExtraction_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | mmg_swMarkerGeneSequencing_16S_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | mmg_swMarkerGeneSequencing_ITS_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | mmg_swPcrAmplification_16S_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20282.001 | Surface water microbe marker gene sequences | mmg_swPcrAmplification_ITS_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20281.001 | Surface water microbe metagenome sequences | mms_swMetagenomeDnaExtraction_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20281.001 | Surface water microbe metagenome sequences | mms_swMetagenomeSequencing_pub | External | NA | 240 | ELF | 5 | external lab processing | 2018-12-31 | BMI lab processing backlog of samples
AOS | NEON.DOM.SITE.DP1.20219.001 | Zooplankton collection | zoo_fieldData_pub | Field | 14 | 30 | FD | 100 | NA | NA | Lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20219.001 | Zooplankton collection | zoo_perVial_pub | External | NA | 240 | ELF | 100 | NA | NA | Lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20219.001 | Zooplankton collection | zoo_taxonomyProcessed_pub | External | NA | 240 | ELF | 100 | NA | NA | Lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20219.001 | Zooplankton collection | zoo_taxonomyRaw_pub | External | NA | 240 | ELF | 100 | NA | NA | Lab contractually has until June 30 to return data
AOS | NEON.DOM.SITE.DP1.20221.001 | Zooplankton DNA barcode | zoo_dnaExtraction_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20221.001 | Zooplankton DNA barcode | zoo_markerGeneSequencing_pub | External | NA | 240 | ELF | 100 | NA | NA
AOS | NEON.DOM.SITE.DP1.20221.001 | Zooplankton DNA barcode | zoo_pcrAmplification_pub | External | NA | 240 | ELF | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00013.001 | Wet deposition chemical analysis | wdp_collection_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00013.001 | Wet deposition chemical analysis | wdp_collectionChem_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00013.001 | Wet deposition chemical analysis | wdp_chemLab_pub | External | NA | 120 | ELF | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00038.001 | Stable isotope concentrations in precipitation | wdi_collection_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00038.001 | Stable isotope concentrations in precipitation | wdi_collectionIso_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00038.001 | Stable isotope concentrations in precipitation | wdi_collectionIsoTest_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00038.001 | Stable isotope concentrations in precipitation | wdi_isoPerSample_pub | External | NA | 90 | ELF | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00101.001 | Particulate mass | dpm_field_pub | Field | 14 | 30 | FD | 100 | NA | NA
TIS | NEON.DOM.SITE.DP1.00101.001 | Particulate mass | dpm_lab_pub | External | NA | 90 | ELF | 100 | NA | NA

## Legend
Latency categories:
FD | Field data only; latency allows time for field ecologists to collect all data in a bout and QA data
DD | Field data and domain lab data only; latency allows time for sample processing (e.g., drying and weighing) and data QA
ELF | Field data plus external analytical facility data, where samples are processed on a rolling basis. May or may not include domain lab processing. Latency allows time for analytical facility to carry out analysis, QA, and upload data.
ELS | Field data plus external analytical facility data, where samples are processed on a bulk basis after completion of the field season. Generally includes domain lab processing. Latency allows time for completion of field collection, domain lab processing, analytical facility processing, and data QA.
OT | One-time sampling; data are collected once per site and will not be provided on a rolling basis.
Legacy data definition | Data we would expect to have received by May 1, 2018, given normal, ongoing operational latencies